## Kaizen checklist
Kaizen checklist - Guidlines
Four weeks prior | Discuss the need for a Kaizen with the sponsor/area manager - Use 90 Day A3 | SPA | Comments | Completed
Select a date for the event (at least one month into the future), confirm with kaizen coach(KC) and kaizen leader(KL)
Determine a preliminary focus of the Kaizen
Is there any data already collected that will help direct the event focus - Process metric
What is the business case & improvement measure - work with lean agent (LA) and KC
Communicate business case and improvement measure to KC, KL and team leader (TL)
Discuss who is being developed as a KC, KL, TL and team manager (TM)
three weeks prior | Observe the entire process, several hours, leaders and team leaders
Observe each position, several hours, leaders and team leaders
Do a detailed drawing of the area (Large)
What is the Baseline Data
Affirm focus of the Kaizen and Business Case
What is the current condition (baseline)
What is the Goal / Hypothesis (target)
Determine if area needs to be 5S-d before the event (prep for improvement)
Complete a work balance table
Review a business case with LA
two weeks prior | Develop agenda
Determine logistics (meeting room, lunch, snacks etc.)
Meet with Mgmt reps - Review mgt roles and presentation
Determine training needs - obs skills, C/O, stdz work etc.
Invite top managment to opening and closing - send outlook invitation
Communicate with all participants, supervisors and crew about the event - date, time, location
Obtain the support of electrical and mechanical maintenance, Safety, IT, engineers etc.
Get name and contact numbers for supporting resources
Contact supporting ressources to discuss expectations during the event
Reserve conference room and/or other work space areas
One week prior | Communicate with crews and supervisors the event is next week - want their support and input
Complete plans for snacks and lunch
Conduct 5S if needed
Conduct Kaizen training if needed
Transparency projector or a computer/projector for power point
VCR-TV, digital camera
flip charts, markers, tape, pencils, stop watches
Forms, standardized work and others if needed
Supporting data
Communicate at the 09:00 meeting that the event is next week, date - times - focus etc.
Buy instant recognition items
Clean conference room and other work spaces.

## Kaizen prep checklist
Kaizen event facilities prep checklist
Kaizen kit items
Items | Req/optional | In kaizen kit | Check - off
Name tag | optional
Participan list | Required
Resource support list | Required
Team list with roles and responsibility | Required
Breakout room assignments | Required
Process information - general and kaizen specific | Required
Forms need (depends on focus on Kaizen) | Required
Observation sheet
Problem countrmeasure forms
Periodic and fluctation tables
Standardize work combination tables
Standardize work charts
Work balance charts
OA observation sheets
Kaizen forms
pads of paper | required | x
clip boards | required | x
pencils | required | x
scotch tape | required | x
earasers | required | x
post it notes | required | x
stop watches | required | x
staplers | optional | x
highliters | optional | x
Team room items
Project A3 or charter | Required
Flip charts, easles and refills | Required
masking tape | optional
permanent and erasable markers | Required
network access | Required
list of printers on network | optional
copier locations | Required
video camera, spare battery and charger | optional
digital camaera | Required
telephone | Required
Main presentation rooms items
Space for all the people | Required
tv/video player | optional
overhead projector | optional
computer projector | Required
space for lunch | Required